## By name
Person | Question | 5th increment______ 10 April,2021 -- 13 April,2021
|  | 1st Day | 2nd Day | 3rd Day | 4th Day
manizha | What did you work on today? | worked on UI of waiter's window attendence | worked on java coding and functionlity of buttons | didn’t do anything | worked on database connection
| What will you work on tomorrow? | the functionality part and database connection | will work on database connection | will connect the table view with databse | will be done with her task by tomorrow
| Do you have any obstacles? | no | no | no | table view values didn't show. Issues with it
maihan | What did you work on today? | worked on the design of menu | functionality of waiter menu | done with the assigned task | done with the assigned task
| What will you work on tomorrow? | will connect it with the admin window | done with her assigned task | done with the assigned task | done with the assigned task
| Do you have any obstacles? | no | no | done with the assigned task | done with the assigned task
seyar | What did you work on today? | worked on fxml part of his assigned part | worked on the design, created table view | database connection | done with his part
| What will you work on tomorrow? | will finish the fxml part and updating of waiter task | database connection | databse connection and functionality part | no
| Do you have any obstacles? | no | no | faced some issues with databse connection | all issues have been sloved
Khalid | What will you work on tomorrow? | didn’t attend the meeting | didn’t attend the meeting | didn’t do anything | didn’t do anything
What will you work on tomorrow?
Do you have any obstacles?