## Sheet1
SPRINT BACKLOG
ID | Backlog task | Assigned to | Start Date | End Date | Priority | Status | Change management notes | Initial estimate | Day 1 | Day 2
1 | As an admin I want to be able to login to the system So, I can access the system | Maihan |  |  | Medium
| Design |  | 24/3/2021 | 25/3/2021 |  | Done |  | 2 Days | 50 | 50
| UI |  | 24/3/2021 | 25/3/2021 |  | Done |  | 2 Days | 50 | 50
| Functionality |  | 24/3/2021 | 25/3/2021 |  | Done |  | 2 Days | 50 | 50
| Testing |  | 24/3/2021 | 25/3/2021 |  | Done |  | 2 Days | 50 | 50
2 | As an admin I want to be able to acess the menu, raw materials list, and customers in one window | Seayar |  |  | Medium
| Design |  | 24/3/2021 | 25/3/2021 |  | Done |  | 2 Days | 50 | 50
| UI |  | 24/3/2021 | 25/3/2021 |  | Done |  | 2 Days | 50 | 50
| Functionality |  | 24/3/2021 | 25/3/2021 |  | Done |  | 2 Days | 50 | 50
| Testing |  | 24/3/2021 | 25/3/2021 |  | Done |  | 2 Days | 50 | 50
3 | As a user I want to be able to register myself in the system So, I can login using my credentials | Khalid |  |  | Top
| Design |  | 24/3/2021 | 25/3/2021 |  | Done |  | 2 Days | 50 | 50
| UI |  | 24/3/2021 | 25/3/2021 |  | Done |  | 2 Days | 50 | 50
| Functionality |  | 24/3/2021 | 25/3/2021 |  | Done |  | 2 Days | 50 | 50
| Testing |  | 24/3/2021 | 25/3/2021 |  | Done |  | 2 Days | 50 | 50
4 | As a user I want to be able to sign in to the system So, I can access the system | Maihan |  |  | Top
| Design |  | 24/3/2021 | 25/3/2021 |  | Done |  | 2 Days | 50 | 50
| UI |  | 24/3/2021 | 25/3/2021 |  | Done |  | 2 Days | 50 | 50
| Functionality |  | 24/3/2021 | 25/3/2021 |  | Done |  | 2 Days | 50 | 50
| Testing |  | 24/3/2021 | 25/3/2021 |  | Done |  | 2 Days | 50 | 50
5 | As a waiter, I want to be able to login to the system so I can access the system resources | Manizha |  |  | Medium
| Design |  | 24/3/2021 | 25/3/2021 |  | Done |  | 2 Days | 50 | 50
| UI |  | 24/3/2021 | 25/3/2021 |  | Done |  | 2 Days | 50 | 50
| Functionality |  | 24/3/2021 | 25/3/2021 |  | Done |  | 2 Days | 50 | 50
| Testing |  | 24/3/2021 | 25/3/2021 |  | Done |  | 2 Days | 50 | 50
6 | Asa user, I want to be able to acess the menu and the available tables in one window | Manizha |  |  | Medium
| Design |  | 24/3/2021 | 25/3/2021 |  | Done |  | 2 Days | 50 | 50
| UI |  | 24/3/2021 | 25/3/2021 |  | Done |  | 2 Days | 50 | 50
| Functionality |  | 24/3/2021 | 25/3/2021 |  | Done |  | 2 Days | 50 | 50
| Testing |  | 24/3/2021 | 25/3/2021 |  | Done |  | 2 Days | 50 | 50