## Sheet1
SPRINT BACKLOG
ID | Backlog task | Assigned to | Start Date | End Date | Priority | Status | Change management notes | Initial estimate | Day 1 | Day 2 | Day 3 | Day 4
1 | As an admin, I want to be able to access the waiters list so I can assign waiters to the reserved tables | Seayar |  |  | Top
| Design |  | 2021-04-05 | 2021-04-08 |  | To Do |  | 4 Days | 0 | 0 | 0 | 0
| UI |  | 2021-04-05 | 2021-04-08 |  | To Do |  | 4 Days | 0 | 0 | 0 | 0
| Functionality |  | 2021-04-05 | 2021-04-08 |  | To Do |  | 4 Days | 0 | 0 | 0 | 0
| Testing |  | 2021-04-05 | 2021-04-08 |  | To Do |  | 4 Days | 0 | 0 | 0 | 0
2 | As an admin, I want to be able to access the waiters list so I can remove waiters from the reserved tables | Seayar |  |  | Top
| Design |  | 2021-04-05 | 2021-04-08 |  | To Do |  | 4 Days | 0 | 0 | 0 | 0
| UI |  | 2021-04-05 | 2021-04-08 |  | To Do |  | 4 Days | 0 | 0 | 0 | 0
| Functionality |  | 2021-04-05 | 2021-04-08 |  | To Do |  | 4 Days | 0 | 0 | 0 | 0
| Testing |  | 2021-04-05 | 2021-04-08 |  | To Do |  | 4 Days | 0 | 0 | 0 | 0
3 | As an admin, I want to be able to access the waiters list so I can refresh waiters list after making changes | Seayar |  |  | Top
| Design |  | 2021-04-05 | 2021-04-08 |  | To Do |  | 4 Days | 0 | 0 | 0 | 0
| UI |  | 2021-04-05 | 2021-04-08 |  | To Do |  | 4 Days | 0 | 0 | 0 | 0
| Functionality |  | 2021-04-05 | 2021-04-08 |  | To Do |  | 4 Days | 0 | 0 | 0 | 0
| Testing |  | 2021-04-05 | 2021-04-08 |  | To Do |  | 4 Days | 0 | 0 | 0 | 0
4 | As an admin, I want to access waiters attendance so I mark them present or absent | Maihan |  |  | Top
| Design |  | 2021-04-05 | 2021-04-08 |  | To Do |  | 4 Days | 0 | 0 | 0 | 0
| UI |  | 2021-04-05 | 2021-04-08 |  | To Do |  | 4 Days | 0 | 0 | 0 | 0
| Functionality |  | 2021-04-05 | 2021-04-08 |  | To Do |  | 4 Days | 0 | 0 | 0 | 0
| Testing |  | 2021-04-05 | 2021-04-08 |  | To Do |  | 4 Days | 0 | 0 | 0 | 0
5 | As an admin, I want to access waiters attendance so I can add the date, starting time, and leaving time | Maihan |  |  | Top
| Design |  | 2021-04-05 | 2021-04-08 |  | To Do |  | 4 Days | 0 | 0 | 0 | 0
| UI |  | 2021-04-05 | 2021-04-08 |  | To Do |  | 4 Days | 0 | 0 | 0 | 0
| Functionality |  | 2021-04-05 | 2021-04-08 |  | To Do |  | 4 Days | 0 | 0 | 0 | 0
| Testing |  | 2021-04-05 | 2021-04-08 |  | To Do |  | 4 Days | 0 | 0 | 0 | 0
6 | As a waiter, I want to be able to login to the system so I can access the system resources | Manizha |  |  | Top
| Design |  | 2021-04-05 | 2021-04-08 |  | To Do |  | 4 Days | 0 | 0 | 0 | 0
| UI |  | 2021-04-05 | 2021-04-08 |  | To Do |  | 4 Days | 0 | 0 | 0 | 0
| Functionality |  | 2021-04-05 | 2021-04-08 |  | To Do |  | 4 Days | 0 | 0 | 0 | 0
| Testing |  | 2021-04-05 | 2021-04-08 |  | To Do |  | 4 Days | 0 | 0 | 0 | 0
7 | As a waiter, I want to be able to access attendance, and reserved tables | Manizha |  |  | Top
| Design |  | 2021-04-05 | 2021-04-08 |  | To Do |  | 4 Days | 0 | 0 | 0 | 0
| UI |  | 2021-04-05 | 2021-04-08 |  | To Do |  | 4 Days | 0 | 0 | 0 | 0
| Functionality |  | 2021-04-05 | 2021-04-08 |  | To Do |  | 4 Days | 0 | 0 | 0 | 0
| Testing |  | 2021-04-05 | 2021-04-08 |  | To Do |  | 4 Days | 0 | 0 | 0 | 0