## By question
Question | Person | 2nd Sprint
|  | 27/3/2021 | 28/3/2021
What did you work on today? | manizha | created the fxml file of customer list window | done with customer list window.
| seyar | worked on the UI of menu window, table view. | done with the functionality of menu window.
| maihan | worked on the design of raw material list | done with the functionality of material list.
| khalid | should collaborate with maihan | not in the meeting
what will you work on tomorrow? | manizha | will work on the functionality of the customer list so admin could see the list of registered customers. And will add another functionality so the admin could delete the customers from the list. | will start working on the next increment
| seyar | will work on some functionality of menu window, for instance, adding and updating the items in the menu. | will start working on the next increment
| maihan | will give funcationailty to her design. for instance, deleting and updating the raw material. | will start working on the next increment
khalid
Do you have any obstacles? | manizha | no | no
| seyar | a lot if his time was comsumed in the UI design. | no
| maihan | can not reach her coworker, khalid. | can not reach khalid.
| khalid | mom is sick, couldn't attend today's meeting. | facing interent issues