## Sheet1
SPRINT BACKLOG
ID | Backlog task | Assigned to | Start Date | End Date | Priority | Status | Change management notes | Initial estimate | Day 1 | Day 2 | Day 3 | Day 4
36 | As a waiter, I want to be able to see my attendance that the admin has checked | Manizha |  |  | Medium
| Design |  | 2021-04-10 | 2021-04-13 |  | To Do |  | 4 Days | 0 | 0 | 0 | 0
| UI |  | 2021-04-10 | 2021-04-13 |  | To Do |  | 4 Days | 0 | 0 | 0 | 0
| Functionality |  | 2021-04-10 | 2021-04-13 |  | To Do |  | 4 Days | 0 | 0 | 0 | 0
| Testing |  | 2021-04-10 | 2021-04-13 |  | To Do |  | 4 Days | 0 | 0 | 0 | 0
37 | As a waiter, I want to be able to see the table I am assigned to so I can serve the guests | Seayar |  |  | Medium
| Design |  | 2021-04-10 | 2021-04-13 |  | To Do |  | 4 Days | 0 | 0 | 0 | 0
| UI |  | 2021-04-10 | 2021-04-13 |  | To Do |  | 4 Days | 0 | 0 | 0 | 0
| Functionality |  | 2021-04-10 | 2021-04-13 |  | To Do |  | 4 Days | 0 | 0 | 0 | 0
| Testing |  | 2021-04-10 | 2021-04-13 |  | To Do |  | 4 Days | 0 | 0 | 0 | 0
38 | As a waiter, I want to be able to see the menu so I can see which dishes are available everyday | Maihan |  |  | Medium
| Design |  | 2021-04-10 | 2021-04-13 |  | To Do |  | 4 Days | 0 | 0 | 0 | 0
| UI |  | 2021-04-10 | 2021-04-13 |  | To Do |  | 4 Days | 0 | 0 | 0 | 0
| Functionality |  | 2021-04-10 | 2021-04-13 |  | To Do |  | 4 Days | 0 | 0 | 0 | 0
| Testing |  | 2021-04-10 | 2021-04-13 |  | To Do |  | 4 Days | 0 | 0 | 0 | 0