## By name
Person | Question | 4th increment______ 5th April,2021 -- 8th April,2021
|  | 1st Day | 2nd Day | 3rd Day | 4th Day
manizha | What did you work on today? | nothing | still struggling to work on her part | woeked on the design of the main page for waiter and add some buttons in the page. design Waiter attendce window. | connected the database with the waiter's attendance
| What will you work on tomorrow? | will work on user window design + java part | will work interface of attendace window | will work on the java and database parts of the waiter's main page | will start working on the 5th increment
| Do you have any obstacles? | assigments in other classes | assigments in other classes | no | no
maihan | What did you work on today? | fxml file of waiters | nothing | worked on functionality of the assigned user stories | done with the his assigned task
| What will you work on tomorrow? | will work on java part | will work on functionality of her part | will work on the connection of the assigend user stories with database | will start working on the 5th increment
| Do you have any obstacles? | no | her laptop is broke | faced some issues with classes and some typing errors | minor issues with connecting the database
seyar | What did you work on today? | creating table for his part | table view connect it database | worked on the interface and functionality of table view | done with the his assigned task
| What will you work on tomorrow? | table view and show the date | will work on fxml part and creat the functionality for it | will work on the half of functionality | will start working on the 5th increment
| Do you have any obstacles? | issue with database part | no | no | no
Khalid | What will you work on tomorrow? | didn’t attend the meeting | didn’t attend the meeting | didn’t attend the meeting | didn’t attend the meeting
| What will you work on tomorrow? | didn’t attend the meeting
| Do you have any obstacles? | didn’t attend the meeting