## Agile Sprint Backlog Blank
PRODUCT BACKLOG
ID | Backlog task | Assigned to | Start Date | End Date | Priority | Status | Change management notes | Initial estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5
[7 empty] | Comments relating to a story point changing, a new story added, or a story removed. | Initial numeric estimate (size) concluded during Sprint Review, Hours | Hours | Hours | Hours | Hours | Hours
1 | As an admin I want to be able to login to the system So, I can access the system | Maihan |  |  | Medium
| Design |  |  |  |  | Done |  | 2 Days | 50 | 50 | 0 | 0 | 0
| UI |  |  |  |  | Done |  | 2 Days | 50 | 50 | 0 | 0 | 0
| Functionality |  |  |  |  | Done |  | 2 Days | 50 | 50 | 0 | 0 | 0
| Testing |  |  |  |  | Done |  | 2 Days | 50 | 50 | 0 | 0 | 0
2 | As an admin I want to be able to acess the menu, raw materials list, waiters list, and customers in one window | Seayar |  |  | Medium
| Design |  |  |  |  | Done |  | 2 Days | 50 | 50 | 0 | 0 | 0
| UI |  |  |  |  | Done |  | 2 Days | 50 | 50 | 0 | 0 | 0
| Functionality |  |  |  |  | Done |  | 2 Days | 50 | 50 | 0 | 0 | 0
| Testing |  |  |  |  | Done |  | 2 Days | 50 | 50 | 0 | 0 | 0
3 | As an admin I want to be able to access the menu So, I can add items to the menu | Seayar |  |  | Top
| Design |  |  |  |  | Done |  | 2 Days | 50 | 50 | 0 | 0 | 0
| UI |  |  |  |  | Done |  | 2 Days | 50 | 50 | 0 | 0 | 0
| Functionality |  |  |  |  | Done |  | 2 Days | 50 | 50 | 0 | 0 | 0
| Testing |  |  |  |  | Done |  | 2 Days | 50 | 50 | 0 | 0 | 0
4 | As an admin I want to be able to access the menu So, I can update the menu | Seayar |  |  | Top
| Design |  |  |  |  | Done |  | 2 Days | 50 | 50 | 0 | 0 | 0
| UI |  |  |  |  | Done |  | 2 Days | 50 | 50 | 0 | 0 | 0
| Functionality |  |  |  |  | Done |  | 2 Days | 50 | 50 | 0 | 0 | 0
| Testing |  |  |  |  | Done |  | 2 Days | 50 | 50 | 0 | 0 | 0
5 | As an admin I want to be able to access the menu So, I can delete items from the menu | Seayar |  |  | Top
| Design |  |  |  |  | Done |  | 2 Days | 50 | 50 | 0 | 0 | 0
| UI |  |  |  |  | Done |  | 2 Days | 50 | 50 | 0 | 0 | 0
| Functionality |  |  |  |  | Done |  | 2 Days | 50 | 50 | 0 | 0 | 0
| Testing |  |  |  |  | Done |  | 2 Days | 50 | 50 | 0 | 0 | 0
6 | As an admin I want to be able to have meals, desserts, and drinks categories in the menu | Manizha |  |  | Top
| Design |  |  |  |  | Done |  | 2 Days | 50 | 50 | 0 | 0 | 0
| UI |  |  |  |  | Done |  | 2 Days | 50 | 50 | 0 | 0 | 0
| Functionality |  |  |  |  | Done |  | 2 Days | 50 | 50 | 0 | 0 | 0
| Testing |  |  |  |  | Done |  | 2 Days | 50 | 50 | 0 | 0 | 0
7 | As an admin I want to be able to access registered customers list So, I can see the list of registered customers | Manizha |  |  | Top
| Design |  |  |  |  | To Do |  | 3 Days | 50 | 50 | 0 | 0 | 0
| UI |  |  |  |  | To Do |  | 3 Days | 50 | 50 | 0 | 0 | 0
| Functionality |  |  |  |  | To Do |  | 3 Days | 50 | 50 | 0 | 0 | 0
| Testing |  |  |  |  | To Do |  | 3 Days | 50 | 50 | 0 | 0 | 0
8 | As an admin I want to be able to access registered customers list So, I can delete registered customers | Manizha |  |  | Top
| Design |  |  |  |  | To Do |  | 3 Days | 50 | 50 | 0 | 0 | 0
| UI |  |  |  |  | To Do |  | 3 Days | 50 | 50 | 0 | 0 | 0
| Functionality |  |  |  |  | To Do |  | 3 Days | 50 | 50 | 0 | 0 | 0
| Testing |  |  |  |  | To Do |  | 3 Days | 50 | 50 | 0 | 0 | 0
9 | As an admin I want to be able to access customers reservation list So, I can see the list of registered customers | Manizha |  |  | Top
| Design |  |  |  |  | Done |  | 2 Days | 50 | 50 | 0 | 0 | 0
| UI |  |  |  |  | Done |  | 2 Days | 50 | 50 | 0 | 0 | 0
| Functionality |  |  |  |  | Done |  | 2 Days | 50 | 50 | 0 | 0 | 0
| Testing |  |  |  |  | Done |  | 2 Days | 50 | 50 | 0 | 0 | 0
10 | As an admin I want to be able to access customers reservations list So, I can delete customers from the list | Manizha |  |  | Top
| Design |  |  |  |  | Done |  | 2 Days | 50 | 50 | 0 | 0 | 0
| UI |  |  |  |  | Done |  | 2 Days | 50 | 50 | 0 | 0 | 0
| Functionality |  |  |  |  | Done |  | 2 Days | 50 | 50 | 0 | 0 | 0
| Testing |  |  |  |  | Done |  | 2 Days | 50 | 50 | 0 | 0 | 0
11 | As an admin I want to be able to access raw materials list So, I can add raw materials to the list | Maihan |  |  | Top
| Design | Maihan |  |  |  | Done |  | 2 Days | 50 | 50 | 0 | 0 | 0
| UI | Maihan |  |  |  | Done |  | 2 Days | 50 | 50 | 0 | 0 | 0
| Functionality | Khalid |  |  |  | Done |  | 2 Days | 50 | 50 | 0 | 0 | 0
| Testing |  |  |  |  | Done |  | 2 Days | 50 | 50 | 0 | 0 | 0
12 | As an admin I want to be able to access raw materials list So, I can delete raw materials from the list | Maihan |  |  | Top
| Design | Maihan |  |  |  | Done |  | 2 Days | 50 | 50 | 0 | 0 | 0
| UI | Maihan |  |  |  | Done |  | 2 Days | 50 | 50 | 0 | 0 | 0
| Functionality | Khalid |  |  |  | Done |  | 2 Days | 50 | 50 | 0 | 0 | 0
| Testing |  |  |  |  | Done |  | 2 Days | 50 | 50 | 0 | 0 | 0
13 | As an admin I want to be able to access raw materials list So, I can update raw materials in the list | Maihan |  |  | Medium
| Design | Khalid |  |  |  | Done |  | 2 Days | 50 | 50 | 0 | 0 | 0
| UI | Khalid |  |  |  | Done |  | 2 Days | 50 | 50 | 0 | 0 | 0
| Functionality | Maihan |  |  |  | Done |  | 2 Days | 50 | 50 | 0 | 0 | 0
| Testing |  |  |  |  | Done |  | 2 Days | 50 | 50 | 0 | 0 | 0
14 | As an admin I want to be able to view the menu So, I can observe the items | Manizha |  |  | Top
| Design |  |  |  |  | To Do |  | 2 Days |  |  | 0 | 0 | 0
| UI |  |  |  |  | To Do |  | 2 Days |  |  | 0 | 0 | 0
| Functionality |  |  |  |  | To Do |  | 2 Days |  |  | 0 | 0 | 0
| Testing |  |  |  |  | To Do |  | 2 Days |  |  | 0 | 0 | 0
15 | As a user I want to be able to register myself in the system So, I can login using my credentials | Khalid |  |  | Top
| Design |  |  |  |  | Done |  | 2 Days | 50 | 50 | 0 | 0 | 0
| UI |  |  |  |  | Done |  | 2 Days | 50 | 50 | 0 | 0 | 0
| Functionality |  |  |  |  | Done |  | 2 Days | 50 | 50 | 0 | 0 | 0
| Testing |  |  |  |  | Done |  | 2 Days | 50 | 50 | 0 | 0 | 0
16 | Asa user, I want to be able to acess the menu and the available tables in one window | Manizha |  |  | Medium
| Design |  |  |  |  | Done |  | 2 Days | 50 | 50 | 0 | 0 | 0
| UI |  |  |  |  | Done |  | 2 Days | 50 | 50 | 0 | 0 | 0
| Functionality |  |  |  |  | Done |  | 2 Days | 50 | 50 | 0 | 0 | 0
| Testing |  |  |  |  | Done |  | 2 Days | 50 | 50 | 0 | 0 | 0
17 | As a user I want to be able to have meals, desserts, and drinks categories in the menu | Manizha |  |  | Top
| Design |  |  |  |  | Done |  | 2 Days | 50 | 50 | 0 | 0 | 0
| UI |  |  |  |  | Done |  | 2 Days | 50 | 50 | 0 | 0 | 0
| Functionality |  |  |  |  | Done |  | 2 Days | 50 | 50 | 0 | 0 | 0
| Testing |  |  |  |  | Done |  | 2 Days | 50 | 50 | 0 | 0 | 0
18 | As a user I want to be able to sign in to the system So, I can access the system | Maihan |  |  | Top
| Design |  |  |  |  | Done |  | 2 Days | 50 | 50 | 0 | 0 | 0
| UI |  |  |  |  | Done |  | 2 Days | 50 | 50 | 0 | 0 | 0
| Functionality |  |  |  |  | Done |  | 2 Days | 50 | 50 | 0 | 0 | 0
| Testing |  |  |  |  | Done |  | 2 Days | 50 | 50 | 0 | 0 | 0
19 | As a user I want to be able to register a table | Seayar
| Design |  |  |  |  | Done |  | 2 Days | 50 | 50 | 0 | 0 | 0
| UI |  |  |  |  | Done |  | 2 Days | 50 | 50 | 0 | 0 | 0
| Functionality |  |  |  |  | Done |  | 2 Days | 50 | 50 | 0 | 0 | 0
| Testing |  |  |  |  | Done |  | 2 Days | 50 | 50 | 0 | 0 | 0
20 | As a user I want to be able to select the date and time of reservation so the host can prepare accordingly | Seayar |  |  | Top
| Design |  |  |  |  | To Do |  | 2 Days | 50 | 50 | 0 | 0 | 0
| UI |  |  |  |  | To Do |  | 2 Days | 50 | 50 | 0 | 0 | 0
| Functionality |  |  |  |  | To Do |  | 2 Days | 50 | 50 | 0 | 0 | 0
| Testing |  |  |  |  | To Do |  | 2 Days | 50 | 50 | 0 | 0 | 0
21 | As a user I want to be able to insert the number of guests per table, so the host can prepare accoedingly | Seayar |  |  | Top
| Design |  |  |  |  | To Do |  | 2 Days | 50 | 50 | 0 | 0 | 0
| UI |  |  |  |  | To Do |  | 2 Days | 50 | 50 | 0 | 0 | 0
| Functionality |  |  |  |  | To Do |  | 2 Days | 50 | 50 | 0 | 0 | 0
| Testing |  |  |  |  | To Do |  | 2 Days | 50 | 50 | 0 | 0 | 0
22 | As a user I want to be able to see the available tables So, I can reserve a table | Seayar |  |  | Top
| Design |  |  |  |  | To Do |  | 2 Days | 0 | 0 | 0 | 0 | 0
| UI |  |  |  |  | To Do |  | 2 Days | 0 | 0 | 0 | 0 | 0
| Functionality |  |  |  |  | To Do |  | 2 Days | 0 | 0 | 0 | 0 | 0
| Testing |  |  |  |  | To Do |  | 2 Days | 0 | 0 | 0 | 0 | 0
23 | As a user I want to be able to see an alert if a table is already reserved so there will not be any conflicts | Seayar |  |  | Top
| Design |  |  |  |  | To Do |  | 2 Days | 0 | 0 | 0 | 0 | 0
| UI |  |  |  |  | To Do |  | 2 Days | 0 | 0 | 0 | 0 | 0
| Functionality |  |  |  |  | To Do |  | 2 Days | 0 | 0 | 0 | 0 | 0
| Testing |  |  |  |  | To Do |  | 2 Days | 0 | 0 | 0 | 0 | 0
24 | As a user I want to be able to access the menu So, I can view the items | Maihan |  |  | Top
| Design |  |  |  |  | To Do |  | 2 Days | 20 | 0 | 0 | 0 | 0
| UI |  |  |  |  | To Do |  | 2 Days | 0 | 30 | 0 | 0 | 0
| Functionality |  |  |  |  | To Do |  | 2 Days | 0 | 0 | 0 | 0 | 0
| Testing |  |  |  |  | To Do |  | 2 Days | 0 | 0 | 0 | 0 | 0
25 | As a user I want to be able to update my credentials So, I can secure my account | Manizha |  |  | Medium
| Design |  |  |  |  | To Do |  | 3 Days | 0 | 0 | 0 | 0 | 0
| UI |  |  |  |  | To Do |  | 3 Days | 0 | 0 | 0 | 0 | 0
| Functionality |  |  |  |  | To Do |  | 3 Days | 0 | 0 | 0 | 0 | 0
| Testing |  |  |  |  | To Do |  | 3 Days | 0 | 0 | 0 | 0 | 0
26 | As an admin, I want to be able to access the waiters list so I can register waiters in the system | Khalid |  |  | Top
| Design |  |  |  |  | To Do |  | 2 Days | 0 | 0 | 0 | 0 | 0
| UI |  |  |  |  | To Do |  | 2 Days | 0 | 0 | 0 | 0 | 0
| Functionality |  |  |  |  | To Do |  | 2 Days | 0 | 0 | 0 | 0 | 0
| Testing |  |  |  |  | To Do |  | 2 Days | 0 | 0 | 0 | 0 | 0
27 | As an admin, I want to be able to access the waiters list so I can remove waiters from the system |  |  |  | Top
| Design |  |  |  |  | To Do |  | 2 Days | 0 | 0 | 0 | 0 | 0
| UI |  |  |  |  | To Do |  | 2 Days | 0 | 0 | 0 | 0 | 0
| Functionality |  |  |  |  | To Do |  | 2 Days | 0 | 0 | 0 | 0 | 0
| Testing |  |  |  |  | To Do |  | 2 Days | 0 | 0 | 0 | 0 | 0
28 | As an admin, I want to be able to access the waiters list so I can assign waiters to the reserved tables |  |  |  | Top
| Design |  |  |  |  | To Do |  | 2 Days | 20 | 0 | 0 | 0 | 0
| UI |  |  |  |  | To Do |  | 2 Days | 0 | 30 | 0 | 0 | 0
| Functionality |  |  |  |  | To Do |  | 2 Days | 0 | 0 | 0 | 0 | 0
| Testing |  |  |  |  | To Do |  | 2 Days | 0 | 0 | 0 | 0 | 0
29 | As an admin, I want to access waiters attendance so I can see who is present |  |  |  | Medium
| Design |  |  |  |  | To Do |  | 2 Days | 0 | 0 | 0 | 0 | 0
| UI |  |  |  |  | To Do |  | 2 Days | 0 | 0 | 0 | 0 | 0
| Functionality |  |  |  |  | To Do |  | 2 Days | 0 | 0 | 0 | 0 | 0
| Testing |  |  |  |  | To Do |  | 2 Days | 0 | 0 | 0 | 0 | 0
30 | As a waiter, I want to be able to login to the system so I can access the system resources | Manizha |  |  | Medium
| Design |  |  |  |  | Done |  | 2 Days | 0 | 0 | 0 | 0 | 0
| UI |  |  |  |  | Done |  | 2 Days | 0 | 0 | 0 | 0 | 0
| Functionality |  |  |  |  | Done |  | 2 Days | 0 | 0 | 0 | 0 | 0
| Testing |  |  |  |  | Done |  | 2 Days | 0 | 0 | 0 | 0 | 0
31 | As a waiter, I want to be able to access attendance, and reserved tables |  |  |  | Medium
| Design |  |  |  |  | To Do |  | 2 Days | 0 | 0 | 0 | 0 | 0
| UI |  |  |  |  | To Do |  | 2 Days | 0 | 0 | 0 | 0 | 0
| Functionality |  |  |  |  | To Do |  | 2 Days | 0 | 0 | 0 | 0 | 0
| Testing |  |  |  |  | To Do |  | 2 Days | 0 | 0 | 0 | 0 | 0
32 | As a waiter, I want to be able to check my attendance so the admin can see my attendance |  |  |  | Medium
| Design |  |  |  |  | To Do |  | 2 Days | 0 | 0 | 0 | 0 | 0
| UI |  |  |  |  | To Do |  | 2 Days | 0 | 0 | 0 | 0 | 0
| Functionality |  |  |  |  | To Do |  | 2 Days | 0 | 0 | 0 | 0 | 0
| Testing |  |  |  |  | To Do |  | 2 Days | 0 | 0 | 0 | 0 | 0
33 | As a waiter, I want to be able to see the table I am assigned to so I can serve the guests |  |  |  | Medium
| Design |  |  |  |  | To Do |  | 2 Days | 0 | 0 | 0 | 0 | 0
| UI |  |  |  |  | To Do |  | 2 Days | 0 | 0 | 0 | 0 | 0
| Functionality |  |  |  |  | To Do |  | 2 Days | 0 | 0 | 0 | 0 | 0
| Testing |  |  |  |  | To Do |  | 2 Days | 0 | 0 | 0 | 0 | 0