## Sheet1
SPRINT BACKLOG
ID | Backlog task | Assigned to | Start Date | End Date | Priority | Status | Change management notes | Initial estimate | Day 1 | Day 2 | Day 3
1 | As an admin I want to be able to access registered customers list So, I can see the list of registered customers | Manizha |  |  | Top
| Design |  | 30/3/2021 | 2021-01-04 |  | To Do |  | 3 Days |  |  | 0
| UI |  | 30/3/2021 | 2021-01-04 |  | To Do |  | 3 Days |  |  | 0
| Functionality |  | 30/3/2021 | 2021-01-04 |  | To Do |  | 3 Days |  |  | 0
| Testing |  | 30/3/2021 | 2021-01-04 |  | To Do |  | 3 Days |  |  | 0
2 | As an admin I want to be able to access registered customers list So, I can delete the registered customers | Manizha |  |  | Top
| Design |  | 30/3/2021 | 2021-01-04 |  | To Do |  | 3 Days |  |  | 0
| UI |  | 30/3/2021 | 2021-01-04 |  | To Do |  | 3 Days |  |  | 0
| Functionality |  | 30/3/2021 | 2021-01-04 |  | To Do |  | 3 Days |  |  | 0
| Testing |  | 30/3/2021 | 2021-01-04 |  | To Do |  | 3 Days |  |  | 0
3 | As an admin I want to be able to view the menu So, I can observe the items | Manizha |  |  | Top
| Design |  | 30/3/2021 | 2021-01-04 |  | To Do |  | 3 Days |  |  | 0
| UI |  | 30/3/2021 | 2021-01-04 |  | To Do |  | 3 Days |  |  | 0
| Functionality |  | 30/3/2021 | 2021-01-04 |  | To Do |  | 3 Days |  |  | 0
| Testing |  | 30/3/2021 | 2021-01-04 |  | To Do |  | 3 Days |  |  | 0
4 | As a user I want to be able to register a table | Seayar |  |  | Top
| Design |  | 30/3/2021 | 2021-01-04 |  | To Do |  | 3 Days |  |  | 0
| UI |  | 30/3/2021 | 2021-01-04 |  | To Do |  | 3 Days |  |  | 0
| Functionality |  | 30/3/2021 | 2021-01-04 |  | To Do |  | 3 Days |  |  | 0
| Testing |  | 30/3/2021 | 2021-01-04 |  | To Do |  | 3 Days |  |  | 0
5 | As a user I want to be able to select the date and time of reservation so the host can prepare accordingly | Seayar |  |  | Top
| Design |  | 30/3/2021 | 2021-01-04 |  | To Do |  | 3 Days |  |  | 0
| UI |  | 30/3/2021 | 2021-01-04 |  | To Do |  | 3 Days |  |  | 0
| Functionality |  | 30/3/2021 | 2021-01-04 |  | To Do |  | 3 Days |  |  | 0
| Testing |  | 30/3/2021 | 2021-01-04 |  | To Do |  | 3 Days |  |  | 0
6 | As a user I want to be able to insert the number of guests per table, so the host can prepare accoedingly | Seayar |  |  | Top
| Design |  | 30/3/2021 | 2021-01-04 |  | To Do |  | 3 Days | 50 | 50 | 0
| UI |  | 30/3/2021 | 2021-01-04 |  | To Do |  | 3 Days | 50 | 50 | 0
| Functionality |  | 30/3/2021 | 2021-01-04 |  | To Do |  | 3 Days | 50 | 50 | 0
| Testing |  | 30/3/2021 | 2021-01-04 |  | To Do |  | 3 Days | 50 | 50 | 0
7 | As a user I want to be able to see the available tables So, I can reserve a table | Seayar |  |  | Top
| Design |  | 30/3/2021 | 2021-01-04 |  | To Do |  | 3 Days | 0 | 0 | 0
| UI |  | 30/3/2021 | 2021-01-04 |  | To Do |  | 3 Days | 0 | 0 | 0
| Functionality |  | 30/3/2021 | 2021-01-04 |  | To Do |  | 3 Days | 0 | 0 | 0
| Testing |  | 30/3/2021 | 2021-01-04 |  | To Do |  | 3 Days | 0 | 0 | 0
8 | As a user I want to be able to see an alert if a table is already reserved so there will not be any conflicts | Seayar |  |  | Top
| Design |  | 30/3/2021 | 2021-01-04 |  | To Do |  | 3 Days | 0 | 0 | 0
| UI |  | 30/3/2021 | 2021-01-04 |  | To Do |  | 3 Days | 0 | 0 | 0
| Functionality |  | 30/3/2021 | 2021-01-04 |  | To Do |  | 3 Days | 0 | 0 | 0
| Testing |  | 30/3/2021 | 2021-01-04 |  | To Do |  | 3 Days | 0 | 0 | 0
9 | As a user I want to be able to access the menu So, I can view the items | Maihan |  |  | Top
| Design |  | 30/3/2021 | 2021-01-04 |  | To Do |  | 3 Days | 0 | 0 | 0
| UI |  | 30/3/2021 | 2021-01-04 |  | To Do |  | 3 Days | 0 | 0 | 0
| Functionality |  | 30/3/2021 | 2021-01-04 |  | To Do |  | 3 Days | 0 | 0 | 0
| Testing |  | 30/3/2021 | 2021-01-04 |  | To Do |  | 3 Days | 0 | 0 | 0
10 | As a user I want to be able to update my credentials So, I can secure my account | Manizha |  |  | Top
| Design |  | 30/3/2021 | 2021-01-04 |  | To Do |  | 3 Days | 0 | 0 | 0
| UI |  | 30/3/2021 | 2021-01-04 |  | To Do |  | 3 Days | 0 | 0 | 0
| Functionality |  | 30/3/2021 | 2021-01-04 |  | To Do |  | 3 Days | 0 | 0 | 0
| Testing |  | 30/3/2021 | 2021-01-04 |  | To Do |  | 3 Days | 0 | 0 | 0
11 | As an admin, I want to be able to access the waiters list so I can register waiters in the system | Khalid |  |  | Top
| Design |  | 30/3/2021 | 2021-01-04 |  | To Do |  | 3 Days | 0 | 0 | 0
| UI |  | 30/3/2021 | 2021-01-04 |  | To Do |  | 3 Days | 0 | 0 | 0
| Functionality |  | 30/3/2021 | 2021-01-04 |  | To Do |  | 3 Days | 0 | 0 | 0
| Testing |  | 30/3/2021 | 2021-01-04 |  | To Do |  | 3 Days | 0 | 0 | 0