## By name
Person | Question | Week: <date>
|  | Monday | Tuesday | Wednesday | Thursday | Friday
Jane | What did you do yesterday?
What will you work on today?
Do you have any obstacles?
Alex | What did you do yesterday?
What will you work on today?
Do you have any obstacles?
Jessica | What did you do yesterday?
What will you work on today?
Do you have any obstacles?
Made by
standuply.com

## By question
Question | Person | 1st sprint
|  | Wednesday | Thursday
What will you do tomorrow? | manizha | will implement the interface in java with its functionality | will start working on the next increment
| seyar | will do the coding of assigned task | will start working on the next increment
| maihan | will work on on her coding bugs | will start working on the next increment
| khalid | will finish the remaining assigned task | he is still struggling with his internet connection therefore he couldn’t finish the assigned task that has been given to him
What did you work on today? | manizha | done with interface of dashboard/ user window | done with the assigned task
| seyar | done with admin page interface | done with the assigned task
| maihan | signup interface and coding | done with the assigned task
| khalid | couldn’t join the meeting. But he texted me that he is still struggling with interface part | done with the assigned task
Do you have any obstacles? | manizha | no | no
| seyar | no | no
| maihan | facing some issues in her code | no
| khalid | got internet isuues,. | stiill facing interent issues