## By name
Person | Question | 3rd increment______ 30,march,2021 -- 1st,april,2021
|  | 1st Day | 2nd Day | 3rd Day
manizha | What did you work on today? | design window customer list, password functionailty | java part of her user story and database. | database and javacode
| What will you work on tomorrow? | coding and fuinctiomnaolty and connect to data base | will work on the error bugging | will work on new increments
| Do you have any obstacles? | no | issues with database connection | errors on code
maihan | What did you work on today? | worked on UI of menu | functionality and connected the database menue | coding part is done
| What will you work on tomorrow? | database connection | java code | will work on new increments
| Do you have any obstacles? | no | no | faced minor issues
seyar | What will you work on tomorrow? | interface of reservation table | connecting database with reservation table | worked on database connection
| What will you work on tomorrow? | connecting to database | error bugging | will work on new increments
| Do you have any obstacles? | no | issues with mysql | worked on issues with manizha
Khalid | What will you work on tomorrow? | didn’t attend the meeting | didn’t attend the meeting | didn’t attend the meeting
| What will you work on tomorrow? | didn’t attend the meeting | didn’t attend the meeting | didn’t attend the meeting
| Do you have any obstacles? | didn’t attend the meeting | didn’t attend the meeting | didn’t attend the meeting